## Program Overview
Metric Name | Current Level | Target Level | Description | Target Description | Status | Responsible Party | Timeline | Priority | Comments | Risk Assessment | Mitigation Plan | Number of People Assigned | Budget | Tools | Challenges
SIEM Capability | Stage 0 | Stage 4 | Basic SIEM monitoring in place, with some alerts | Full automation of detection & response | In Progress | SIEM Engineer |  | High | Need to integrate threat feeds | High
SOAR Capability | Stage 1 | Stage 2 | Automation and enrichment to support investigations and response | 70% automated reposne for teir 1 investigations | In Progress | SOAR Engineer |  | High | Automation requires integration with SIEM
SOC Operations, Response, and Threat Hunting | Stage 3 | Stage 4 | Advanced playbooks, some manual responses | Full automation of response workflows | On Track | Incident Response Team |  | High |  | Medium
Log Collection | Stage 1 | Stage 3 | Limited to basic network device logging | Coverage for all critical assets | At Risk | SIEM Engineer |  | Medium | Need additional resources to add VPN logging | Low
Threat Intelligence | Stage 0 | Stage 3 | No integration of threat intelligence feeds | Integrate at least two commercial threat feeds | Not Started | Threat Intel |  | High | Identifying appropriate threat feeds | Low
Insider Risk | Stage 0 | Stage 2 | Active monitoring, response plan in place, partnership across busniss | Proactive response, streamlined investigations | Not Started | Insider Threat Lead |  | High |  | High
Team | Stage 2 | Stage 4 | Overall team capabilities needed to meet current and future threat landscapes | All programs staffed at 80% or higher, training in place for development, retention programs in place, on going process improvements and program development | In Progress | Leadership Team |  | High |  | High
Compliance/Audit Reddiness | Stage1 | Stage 3 | Ability to meet all legal and compliance requirements, provide audit evedince effcentely, and in timely manner | Automation in place for self-service style audit evedience collection, dashboards for compliance monitoring, minimal effort required to support audits | In Progress | SIEM Engineer |  | Medium |  | Medium
Stage | Description
Stage 0 - Initial | General Awareness of the topic but no initiatives are in place.
Stage 1 - Minimal | There are basic things in place to meet an initial requirement. This is entry level and more work is needed.
Stage 2 - Procedural | This area has begun to evolve and improvements have been made. At this level the initiative begins to exceed the minimum requirement.
Stage 3 - Innovative | This area begins to see advanced improvements and is well established. At this level the initiative is considered advanced and exceeds the requirement.
Stage 4 - Leading | This area is well established and mature, only basic maintenance is required. At this level the initiative is cutting edge and beyond industry standards.

## SIEM
Capability | Sub-Item | Description | Availability | Current Level | Target Level | Owner | Improvement Plan | Use Cases
Detection Capabilities | Malware Detection | Ability to detect various threats, such as malware, anomalies, and insider threats using the SIEM. Includes correlation of data from multiple sources to identify complex attack patterns. | Partially Available | Stage 2 - Procedural |  | SIEM Team | Improve detection rules for insider threats; Enhance correlation capabilities | Threat Detection, Compliance
Detection Capabilities | Anomaly Detection | Ability to detect anomalies in user behavior or network activity that may indicate a security incident. | Partially Available | Stage 2 - Procedural |  | SIEM Team | Improve anomaly detection models; Enhance data quality | Threat Detection, Compliance
Detection Capabilities | Insider Threat Detection | Identify potential insider threats through monitoring user activity and behaviors that deviate from norms. | Partially Available | Stage 2 - Procedural |  | SIEM Team | Enhance correlation with HR data; Develop insider threat detection rules | Threat Detection, Compliance
Threat Hunting | IOC Search | Ability to proactively search for indicators of compromise (IOCs) to identify potential threats. | Available | Stage 3 - Innovative |  | Threat Intel Team | Increase frequency of IOC searches; Integrate new threat feeds | Threat Detection, Incident Response
Threat Hunting | Behavioral Analysis | Analyze user and entity behaviors to identify deviations that may indicate threats. | Available | Stage 3 - Innovative |  | Threat Intel Team | Develop more advanced behavioral analysis models | Threat Detection, Incident Response
Threat Hunting | Threat Hypothesis Testing | Formulate and test hypotheses to uncover sophisticated threats that evade detection. | Available | Stage 3 - Innovative |  | Threat Intel Team | Develop more advanced threat hunting playbooks | Threat Detection, Incident Response
Custom Dashboards | Executive Dashboard | Provide a high-level overview of security posture tailored for executive stakeholders. | Available | Stage 3 - Innovative |  | SIEM Admin Team | Create dashboards for executive reporting | Visibility, Reporting, Compliance
Custom Dashboards | Analyst Dashboard | Detailed dashboards for SOC analysts to monitor ongoing incidents and security metrics. | Available | Stage 3 - Innovative |  | SIEM Admin Team | Develop more user-specific dashboards | Visibility, Reporting, Compliance
Custom Dashboards | Incident Response Dashboard | Dashboards designed to support incident response activities, including alerts and threat context. | Available | Stage 3 - Innovative |  | SIEM Admin Team | Enhance dashboards with more real-time data | Incident Response, Threat Detection
Alert Creation | Rule-Based Alerts | Create alerts based on specific predefined rules to detect suspicious activities. | Available | Stage 3 - Innovative |  | SOC Team | Refine alert thresholds to reduce false positives | Threat Detection, Incident Response
Alert Creation | Threshold Alerts | Generate alerts when certain thresholds are exceeded, indicating potential anomalies. | Available | Stage 3 - Innovative |  | SOC Team | Implement alert prioritization based on risk | Threat Detection, Incident Response
Alert Creation | Escalation Workflows | Define workflows to escalate alerts based on severity and risk assessment. | Available | Stage 3 - Innovative |  | SOC Team | Automate escalation processes to improve response time | Threat Detection, Incident Response
Alert Creation | Machine Learning Alerts | Utilize machine learning models to generate alerts for anomalous activities that may indicate threats. | Available | Stage 3 - Innovative |  | SOC Team | Develop and train machine learning models for anomaly detection | Threat Detection, Incident Response
Admin Functions | User Management | Manage user accounts, roles, and permissions within the SIEM environment. | Available | Stage 3 - Innovative |  | SIEM Admin Team | Streamline user role assignment; Periodically review user access | System Management, Compliance
Admin Functions | Log Retention | Manage retention policies for logs to meet compliance and operational needs. | Available | Stage 3 - Innovative |  | SIEM Admin Team | Automate log retention based on policy changes | System Management, Compliance
Admin Functions | Role-Based Access Control | Implement and manage role-based access control for the SIEM to ensure appropriate permissions. | Available | Stage 3 - Innovative |  | SIEM Admin Team | Automate audit logging for role changes | System Management, Compliance
Admin Functions | Configuration Auditing | Regularly audit configuration changes to ensure compliance and adherence to best practices. | Available | Stage 3 - Innovative |  | SIEM Admin Team | Implement automated configuration audits | System Management, Compliance
Upkeep | Software Updates | Regularly update SIEM software to ensure security and access to new features. | Available | Stage 2 - Procedural |  | SIEM Maintenance Team | Automate routine maintenance tasks; Schedule regular updates | System Stability, Compliance
Upkeep | Performance Monitoring | Monitor SIEM performance to identify bottlenecks and optimize system efficiency. | Available | Stage 2 - Procedural |  | SIEM Maintenance Team | Implement proactive health checks | System Stability, Compliance
Upkeep | Health Checks | Perform regular system health checks to ensure all components are functioning properly. | Available | Stage 2 - Procedural |  | SIEM Maintenance Team | Ensure regular health check procedures are documented | System Stability, Compliance
Upkeep | Backup & Recovery | Ensure SIEM data is backed up and recovery procedures are in place in case of failure. | Available | Stage 2 - Procedural |  | SIEM Maintenance Team | Ensure regular backup and recovery tests | System Stability, Compliance
Threat Intel Feed Search | Feed Integration | Integrate multiple threat intelligence feeds into the SIEM for comprehensive threat visibility. | Available | Stage 3 - Innovative |  | Threat Intel Team | Integrate additional threat feeds | Threat Detection, Threat Intelligence
Threat Intel Feed Search | Threat Correlation | Correlate threat intelligence with internal activity to identify potential compromises. | Available | Stage 3 - Innovative |  | Threat Intel Team | Automate correlation processes to improve efficiency | Threat Detection, Threat Intelligence
Threat Intel Feed Search | Automated Enrichment | Automatically enrich internal alerts with data from threat intelligence feeds. | Available | Stage 3 - Innovative |  | Threat Intel Team | Automate enrichment of threat intelligence data | Threat Detection, Threat Intelligence
Threat Intel Feed Search | Threat Actor Profiling | Profile threat actors based on correlated intelligence and historical data. | Available | Stage 3 - Innovative |  | Threat Intel Team | Expand threat actor profiling capabilities | Threat Detection, Threat Intelligence
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
SIEM Monitoring | Initial Implementation | Deploying basic SIEM monitoring for threat detection, focusing on key log sources. | Log Collection Expansion | Critical Assets Logging | Expand log collection to include critical assets like firewalls, routers, and servers. | Alerting Configuration | Correlation Alerts | Create correlation rules to identify suspicious activities across data sources.
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Data Normalization | Data Model Setup | Implement a data model to normalize incoming log data for consistent analysis. | Dashboard Creation | Executive Dashboard | Develop an executive-level dashboard for high-level SIEM metrics. | Log Retention Policy | Retention Configuration | Configure log retention policies to meet regulatory compliance requirements.
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Threat Intelligence Integration | Feed Integration | Integrate commercial threat feeds with SIEM for enriched alert context. | Advanced Alerting | Custom Use Cases | Develop custom use cases focusing on critical behaviors like privilege escalation. | User Behavior Analytics (UBA) | Behavioral Baselines | Implement UBA to establish baselines and flag deviations.
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Incident Workflow Integration | SOAR Integration | Integrate SIEM with SOAR for automated response workflows. | Tuning Alerts | False Positive Reduction | Tune alert rules to reduce false positives and improve response efficiency. | Operationalizing Threat Feeds | Use Case Development | Develop use cases to operationalize threat feeds and identify IoCs (Indicators of Compromise).
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## SOAR
Capability | Sub-Item | Description | Availability | Current Level | Target Level | Owner | Improvement Plan | Use Cases
Playbook Development | Standard Playbooks | Develop standardized playbooks for common incidents to ensure consistent and repeatable response actions. | Available | Stage 2 - Procedural |  | SOAR Team | Review and refine existing playbooks; Create more comprehensive response actions | Incident Response, Threat Detection
Playbook Development | Custom Playbooks | Develop playbooks tailored for specific business units or unique threats to increase response efficacy. | Available | Stage 3 - Innovative |  | SOAR Team | Collaborate with stakeholders for custom requirements; Improve flexibility of playbooks | Incident Response, Customization
Playbook Development | Playbook Testing | Regularly test and validate playbooks to ensure they perform as expected in different scenarios. | Partially Available | Stage 2 - Procedural |  | SOAR Team | Implement scheduled playbook tests; Document and fix gaps identified during tests | Incident Readiness, Quality Control
Case Management | Incident Tracking | Track and document incidents within the SOAR platform, including categorization, status, and historical data. | Available | Stage 3 - Innovative |  | Incident Response Team | Improve categorization accuracy; Automate incident status updates | Incident Response, Reporting
Case Management | Investigation Collaboration | Facilitate collaboration between SOC analysts during investigations, including note-sharing and task assignments. | Available | Stage 3 - Innovative |  | SOC Team | Implement more efficient collaboration tools; Develop shared incident workspaces | Incident Response, Team Collaboration
Case Management | Post-Incident Review | Conduct post-incident reviews to analyze the root cause and response effectiveness. | Available | Stage 2 - Procedural |  | Incident Response Team | Automate reporting templates for reviews; Improve documentation process | Incident Analysis, Process Improvement
Integration Management | SIEM Integration | Integrate SOAR with SIEM to trigger automated responses based on detected alerts. | Available | Stage 3 - Innovative |  | SOAR Team | Improve alert enrichment from SIEM; Automate response triggers | Threat Detection, Automated Response
Integration Management | Endpoint Security Integration | Integrate SOAR with endpoint security tools to provide context during incident response actions. | Partially Available | Stage 2 - Procedural |  | SOAR Team | Expand integration to additional endpoint tools; Develop enriched response actions | Endpoint Threat Detection, Response
Integration Management | Threat Intelligence Integration | Integrate SOAR with threat intelligence feeds to provide enriched context for incidents and response actions. | Available | Stage 3 - Innovative |  | Threat Intel Team | Improve threat feed integration; Automate enrichment during playbook execution | Threat Intelligence, Incident Context
Automated Actions | Containment Actions | Automate containment steps, such as isolating compromised hosts, based on predefined conditions. | Available | Stage 3 - Innovative |  | SOC Team | Refine conditions for containment; Develop fallback manual procedures | Threat Containment, Incident Response
Automated Actions | Threat Intelligence Enrichment | Automatically enrich incidents with threat intelligence data, including IOCs and known malicious actors. | Available | Stage 3 - Innovative |  | Threat Intel Team | Integrate additional threat feeds; Automate IOC matching | Threat Detection, Threat Enrichment
Automated Actions | Notification and Escalation | Automate notifications and escalations to appropriate teams when incidents meet predefined criteria. | Available | Stage 3 - Innovative |  | Incident Response Team | Implement flexible escalation workflows; Review notification efficiency | Incident Response, Team Coordination
Reporting and Metrics | Incident Metrics | Track key metrics related to incident response, such as mean time to detect (MTTD) and mean time to respond (MTTR). | Available | Stage 3 - Innovative |  | Reporting Team | Automate metric collection from incidents; Improve visualization in reports | Incident Response, Metrics Tracking
Reporting and Metrics | Compliance Reporting | Automate the generation of reports needed for compliance audits and regulatory requirements. | Available | Stage 3 - Innovative |  | Compliance Team | Develop automated compliance report templates; Schedule regular report exports | Compliance, Regulatory Reporting
Reporting and Metrics | Executive Summary | Create executive summary reports that provide high-level views of the security posture and major incidents. | Available | Stage 3 - Innovative |  | Reporting Team | Collaborate with executives for report requirements; Automate dashboard updates | Executive Reporting, Visibility
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## SOC Ops
Capability | Sub-Item | Description | Availability | Maturity Level | Target Level | Owner | Improvement Plan | Use Cases
Incident Detection | Security Monitoring | Monitor security events across the network, endpoints, and applications to detect potential incidents. | Available | Stage 3 - Innovative |  | Security Operations Team | Enhance monitoring coverage for critical systems; Expand detection rules | Threat Detection, Incident Response
Incident Detection | Alert Analysis | Analyze alerts generated by SIEM and other tools to determine potential incidents that require action. | Available | Stage 3 - Innovative |  | SOC Team | Improve alert triage processes; Develop analyst training programs | Threat Detection, Incident Response
Incident Detection | Anomaly Detection | Identify anomalies in user or system behavior that may indicate malicious activity. | Partially Available | Stage 2 - Procedural |  | Security Operations Team | Implement machine learning for better anomaly detection; Enhance data quality | Threat Detection, User Behavior Monitoring
Incident Response | Triage and Investigation | Conduct initial triage and in-depth investigation of incidents to assess impact and determine response actions. | Available | Stage 3 - Innovative |  | Incident Response Team | Standardize investigation procedures; Develop better triage guidelines | Incident Response, Threat Analysis
Incident Response | Containment | Contain incidents by isolating affected systems and minimizing damage while preserving evidence. | Available | Stage 3 - Innovative |  | Incident Response Team | Automate containment where possible; Develop manual fallback procedures | Threat Containment, Incident Handling
Incident Response | Eradication | Remove malicious elements from affected systems and environments to ensure complete incident resolution. | Available | Stage 2 - Procedural |  | Incident Response Team | Streamline eradication processes; Improve toolsets for faster eradication | Threat Removal, System Recovery
Incident Response | Recovery | Restore affected systems and services to normal operation, ensuring no remnants of the threat remain. | Available | Stage 2 - Procedural |  | IT Recovery Team | Develop detailed recovery procedures; Test recovery regularly | System Recovery, Service Restoration
Incident Response | Post-Incident Review | Conduct reviews after incident resolution to determine root causes, lessons learned, and improve processes. | Available | Stage 2 - Procedural |  | Incident Response Team | Automate post-incident reporting; Develop a consistent review template | Process Improvement, Incident Analysis
Threat Intelligence Utilization | IOC Matching | Leverage indicators of compromise (IOCs) from threat intelligence feeds to identify threats in the environment. | Available | Stage 3 - Innovative |  | Threat Intel Team | Automate IOC ingestion and matching; Expand threat intelligence sources | Threat Detection, Intelligence Integration
Threat Intelligence Utilization | Threat Actor Analysis | Identify and analyze threat actors responsible for incidents to understand motivations, tactics, and potential future actions. | Partially Available | Stage 2 - Procedural |  | Threat Intel Team | Improve analysis of threat actor profiles; Integrate historical incident data | Threat Analysis, Threat Profiling
Threat Intelligence Utilization | Threat Landscape Awareness | Maintain awareness of the evolving threat landscape, including emerging threats and attack techniques. | Available | Stage 3 - Innovative |  | Threat Intel Team | Develop regular threat landscape reports; Improve analyst awareness programs | Threat Intelligence, Risk Management
Collaboration and Coordination | Internal Communication | Facilitate communication among internal teams during incident response, including IT, legal, and management. | Available | Stage 3 - Innovative |  | Incident Response Team | Implement streamlined communication channels; Develop escalation paths | Incident Coordination, Team Collaboration
Collaboration and Coordination | External Communication | Coordinate with external entities, such as vendors, regulators, and law enforcement, during incidents. | Available | Stage 2 - Procedural |  | Incident Response Team | Develop external communication procedures; Build relationships with law enforcement | Incident Reporting, Regulatory Compliance
Collaboration and Coordination | Stakeholder Engagement | Keep key stakeholders informed during incidents, including status updates and expected impact. | Available | Stage 2 - Procedural |  | Incident Response Team | Develop stakeholder engagement templates; Automate status updates | Executive Reporting, Incident Transparency
Metrics and Reporting | Incident Metrics | Track and report key metrics, such as the number of incidents, response times, and severity levels. | Available | Stage 3 - Innovative |  | Reporting Team | Automate incident metrics collection; Improve data visualization | Incident Response, Metrics Tracking
Metrics and Reporting | SLA Adherence | Monitor adherence to Service Level Agreements (SLAs) for incident response to ensure timely action. | Available | Stage 2 - Procedural |  | SOC Team | Develop SLA tracking dashboards; Automate SLA breach notifications | Service Assurance, Incident Management
Metrics and Reporting | Continuous Improvement | Measure the effectiveness of incident response efforts and identify areas for improvement. | Available | Stage 2 - Procedural |  | Incident Response Team | Develop improvement plans based on post-incident reviews; Implement regular process audits | Process Improvement, Quality Assurance
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## Log Collection
Data Source Name | Log Type | Availability | Required? | Compliance Requirements | Log Volume (GB/day) | Data Quality | Retention Period | Use Cases | Current Issues | Improvement Plan | Owner | Collection Status | Data Integration Status | Data Format | Maturity Level | Target Level
Firewall Logs | Network | Available | Yes |  | 50 | High | 1 Year | Threat Detection, Compliance | None | N/A | Network Team | Automated | Integrated | Syslog | Stage 3 - Innovative
VPN Logs | Security | Partially | Yes |  | 10 | Medium | 90 Days | Access Auditing, User Monitoring | Missing logs from some devices | Add additional VPN log collectors | Security Team | Manual | Not Integrated | JSON | Stage 1 - Minimal
DNS Logs | Network | Unavailable | Yes |  | Unknown | N/A | N/A | Threat Detection | No collection mechanism | Implement centralized DNS logging | Network Operations | Not Collected | Not Integrated | N/A | Stage 0 - Initial
Router & Switch Logs | Network | Partially | Yes |  | 20 | Medium | 180 Days | Network Monitoring, Troubleshooting | Missing some device logs | Standardize logging across devices | Network Team | Manual | Not Integrated | Syslog | Stage 1 - Minimal
Proxy Logs | Network | Available | Yes |  | 15 | High | 1 Year | Web Usage Monitoring, Threat Detection | None | N/A | Security Team | Automated | Integrated | CSV | Stage 3 - Innovative
Network IDS/IPS Logs | Security | Available | Yes |  | 25 | High | 1 Year | Intrusion Detection, Threat Prevention | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative
NetFlow/SFlow | Network | Available | Yes |  | 30 | Medium | 90 Days | Traffic Analysis | Data volume is very high | Implement filtering to reduce volume | Network Team | Automated | Not Integrated | NetFlow | Stage 2 - Procedural
Endpoint Security (EDR) | Security | Available | Yes |  | 100 | High | 180 Days | Threat Detection, Response | Data duplication | Streamline logging to reduce redundancy | Endpoint Team | Automated | Integrated | JSON | Stage 3 - Innovative
Antivirus/Anti-Malware Logs | Security | Available | Yes |  | 5 | High | 90 Days | Malware Detection | None | N/A | Endpoint Team | Automated | Integrated | CSV | Stage 3 - Innovative
Patch Management Logs | Endpoint | Available | Yes |  | 2 | Medium | 180 Days | Vulnerability Management | Inconsistent logging from some endpoints | Standardize patch reporting | Endpoint Team | Manual | Partially Integrated | CSV | Stage 2 - Procedural
Web Server Logs | Application | Available | No |  | 20 | Medium | 30 Days | Debugging, Monitoring | Incomplete log entries | Standardize logging practices | DevOps Team | Automated | Not Integrated | CSV | Stage 1 - Minimal
Application Server Logs | Application | Available | Yes |  | 25 | Medium | 90 Days | Application Monitoring, Troubleshooting | None | N/A | Application Team | Automated | Partially Integrated | JSON | Stage 2 - Procedural
Database Audit Logs | Application | Available | Yes |  | 15 | High | 1 Year | Compliance, User Activity Tracking | None | N/A | Database Admin Team | Automated | Integrated | JSON | Stage 3 - Innovative
Authentication Services Logs | Identity | Available | Yes |  | 10 | High | 1 Year | User Authentication, Access Control | None | N/A | Identity Management Team | Automated | Integrated | CSV | Stage 3 - Innovative
Identity Provider Logs | Identity | Available | Yes |  | 8 | High | 180 Days | Authentication Tracking, MFA | None | N/A | Identity Team | Automated | Integrated | JSON | Stage 3 - Innovative
Privileged Access Management Logs | Identity | Available | Yes |  | 5 | High | 90 Days | Privileged Session Monitoring | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative
SIEM System Logs | Security | Available | Yes |  | 10 | High | 1 Year | System Monitoring, Alerting | None | N/A | SIEM Admin Team | Automated | Integrated | JSON | Stage 3 - Innovative
SOAR Logs | Security | Available | Yes |  | 5 | High | 90 Days | Incident Response Automation | None | N/A | Security Operations | Automated | Integrated | JSON | Stage 3 - Innovative
Vulnerability Scanners | Compliance | Available | Yes |  | 15 | High | 1 Year | Vulnerability Management, Compliance | None | N/A | Security Team | Automated | Integrated | CSV | Stage 3 - Innovative
CloudTrail (AWS) | Cloud | Available | Yes |  | 15 | High | 180 Days | Cloud Activity Monitoring, Compliance | None | N/A | Cloud Team | Automated | Integrated | JSON | Stage 3 - Innovative
GuardDuty (AWS) | Cloud Security | Available | Yes |  | 8 | High | 90 Days | Anomaly Detection in Cloud | Limited to certain accounts | Expand to cover all accounts | Cloud Security Team | Automated | Partially Integrated | JSON | Stage 2 - Procedural
Storage Access Logs (S3) | Cloud | Available | Yes |  | 5 | High | 90 Days | Data Access Monitoring | None | N/A | Cloud Team | Automated | Integrated | JSON | Stage 3 - Innovative
Badge Access Logs | Physical | Available | No |  | 5 | High | 1 Year | Physical Security Monitoring | None | N/A | Facilities Team | Automated | Not Integrated | CSV | Stage 1 - Minimal
Enterprise Resource Planning (ERP) System Logs (SAP) | Business | Available | Yes |  | 12 | Medium | 1 Year | Financial Monitoring, Compliance | None | N/A | Business Systems Team | Automated | Partially Integrated | JSON | Stage 2 - Procedural
CRM Logs (Salesforce) | Business | Available | No |  | 10 | Medium | 90 Days | Customer Activity Tracking | None | N/A | Sales Team | Automated | Not Integrated | CSV | Stage 1 - Minimal
Threat Intelligence Feeds | Security | Available | Yes |  | N/A | High | Real-time | Threat Detection, Indicator Matching | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative
Data Loss Prevention Logs | Security | Available | Yes |  | 5 | High | 90 Days | Sensitive Data Protection | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## Threat Intel
Capability | Sub-Item | Description | Availability | Maturity Level | Target Level | Owner | Improvement Plan | Use Cases
Threat Intelligence Gathering | Basic Threat Intelligence | Collect and aggregate threat intelligence from various sources, such as open-source feeds and vendor reports. | Available | Stage 2 - Procedural |  | Threat Intel Team | Expand threat intelligence sources; Automate data collection | Threat Detection, Situational Awareness
Threat Intelligence Gathering | Brand Monitoring | Monitor for mentions of the organization's brand across the internet to detect potential brand misuse or threats. | Partially Available | Stage 2 - Procedural |  | Threat Intel Team | Integrate additional brand monitoring tools; Develop reporting process for brand threats | Brand Protection, Threat Detection
Threat Intelligence Gathering | Specific Advisory Monitoring | Track advisories specific to the organization's industry, region, or technology stack to stay updated on emerging threats. | Available | Stage 3 - Innovative |  | Threat Intel Team | Improve advisory filtering to reduce noise; Automate advisory distribution | Threat Intelligence, Risk Management
Threat Intelligence Analysis | IOC Analysis | Analyze indicators of compromise (IOCs) such as IP addresses, domains, and hashes to determine relevance and potential threats. | Available | Stage 3 - Innovative |  | Threat Intel Team | Automate IOC correlation with internal data; Expand IOC enrichment capabilities | Threat Detection, Incident Response
Threat Intelligence Analysis | Threat Actor Profiling | Profile known threat actors, including motivations, tactics, and past activities, to understand potential threats to the organization. | Partially Available | Stage 2 - Procedural |  | Threat Intel Team | Expand historical incident data integration; Improve actor profile accuracy | Threat Analysis, Threat Profiling
Threat Intelligence Analysis | Targeted Use Case Development | Develop specific use cases for threat intelligence that align with business needs, such as protecting VIPs or critical assets. | Partially Available | Stage 3 - Innovative |  | Threat Intel Team | Collaborate with business units to identify targeted use cases; Refine intelligence requirements | Threat Detection, Business Alignment
Threat Intelligence Reporting | Executive Reports | Create high-level threat intelligence reports for executives, summarizing key risks, trends, and emerging threats. | Available | Stage 3 - Innovative |  | Reporting Team | Standardize executive report templates; Develop automated report generation capabilities | Executive Awareness, Strategic Planning
Threat Intelligence Reporting | Threat Landscape Reports | Provide detailed analysis of the evolving threat landscape, including notable incidents and emerging threat vectors. | Available | Stage 3 - Innovative |  | Threat Intel Team | Develop regular threat landscape reports; Improve data visualization | Threat Intelligence, Situational Awareness
Threat Intelligence Reporting | Advisory Summaries | Generate summaries of relevant threat advisories and distribute them to appropriate teams for awareness and action. | Available | Stage 2 - Procedural |  | Threat Intel Team | Automate advisory summary distribution; Create targeted advisory categories | Threat Awareness, Risk Management
Threat Intelligence Utilization | Threat Correlation | Correlate gathered threat intelligence with internal security data to identify potential incidents and compromises. | Available | Stage 3 - Innovative |  | SOC Team | Automate threat correlation processes; Expand correlation rules | Threat Detection, Incident Response
Threat Intelligence Utilization | Brand Protection Actions | Take action based on identified brand threats, such as takedown requests or legal measures to mitigate reputational risks. | Partially Available | Stage 2 - Procedural |  | Threat Intel Team | Develop standardized response procedures for brand threats; Improve takedown efficiency | Brand Protection, Incident Management
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## Insider Risk
Category | Sub-Item | Description | Availability | Maturity Level | Target Level | Owner | Improvement Plan | Use Cases
Administrative | Corporate Policies | Corporate policies in place that support monitoring, investigations, and remediation efforts. Policies are reviewed for changes, and feedback is provided to strengthen and enhance policies. | Available | Stage 0 - Initial |  | HR & Compliance Team | Develop a feedback loop to improve policies based on incidents | Policy Enforcement, Compliance Monitoring
Administrative | Partnerships | Partnerships in place with Legal, Employee Relations, and Privacy teams. Briefed on new legal and regulatory requirements. Ensure processes to remediate Insider Threat activity are in place. | Partially Available | Stage 1 - Minimal |  | HR, Legal, Privacy Teams | Expand partnerships to additional departments; Regularize briefing schedule | Cross-Department Collaboration, Compliance
Administrative | Senior Leadership Engagement | Obtain support from Senior Leadership team, provide regular updates, and solicit feedback to enhance insider threat initiatives. | Available | Stage 2 - Procedural |  | Insider Threat Team | Develop formal engagement plan for regular leadership updates | Stakeholder Engagement, Executive Support
Administrative | Logging Standards and Collection | Relevant logs are being collected to support use cases. Log sources are reviewed and updated regularly. Logging standards are also reviewed regularly. | Available | Stage 3 - Innovative |  | Security Operations Team | Automate log collection; Implement standardized logging guidelines | Data Collection, Threat Detection
Administrative | Threat Landscape Documentation | Threat landscape is well documented and reviewed at regular intervals to keep up with emerging threats and changes. | Available | Stage 4 - Leading |  | Threat Intel Team | Develop visualization of threat landscape trends; Increase review frequency | Situational Awareness, Risk Assessment
Tools | Data Loss Prevention (DLP) | Data Loss Prevention tools are in place and actively monitored. The alert portfolio is reviewed regularly and the tool's effectiveness is tested on a consistent basis. | Available | Stage 2 - Procedural |  | IT Security Team | Expand DLP coverage; Automate regular tool testing | Data Protection, Threat Detection
Tools | User Behavior Analytics (UBA/UEBA) | User Behavior Analytics tools are in place to monitor behavior. Alerts are reviewed and the tool is tested regularly for effectiveness. | Available | Stage 3 - Innovative |  | IT Security Team | Integrate UBA with other data sources; Improve anomaly detection algorithms | Insider Threat Detection, Anomaly Detection
Tools | Risk-Based Alerting (RBA) | Risk-Based Alerting framework is in place. Risk rules are reviewed and tested regularly to ensure effectiveness. | Partially Available | Stage 3 - Innovative |  | Security Operations Team | Expand risk-based alerting rules; Regularize risk rule reviews | Threat Prioritization, Incident Response
Custom Detections | Sensitive File Exfiltration | Custom detections are being developed to monitor for unauthorized file exfiltration. | Available | Stage 2 - Procedural |  | Insider Threat Team | Expand monitoring to additional data types; Improve detection sensitivity | Data Protection, Incident Response
Custom Detections | Rogue Administrator Activity | Custom detections are developed to monitor administrator actions that are out of scope, such as unusual user activity or potentially malicious changes. | Partially Available | Stage 3 - Innovative |  | Insider Threat Team | Develop anomaly-based detections; Expand monitoring of privileged accounts | Privilege Misuse Detection, Threat Detection
Custom Detections | Unusual File Access | Custom detections monitor unusual file access patterns, including access by unauthorized users or behaviors that deviate from the norm. | Available | Stage 2 - Procedural |  | Insider Threat Team | Automate alerting for suspicious file access; Develop a baseline of normal activity | Threat Detection, Data Security
Custom Detections | High Turnover Departments | Monitoring departments with high turnover rates for potential insider threats and anomalous activity. | Available | Stage 2 - Procedural |  | Insider Threat Team | Implement proactive detection for high-risk departments; Regularize reviews | Risk Management, Insider Threat Detection
Custom Detections | Compromised Account Detection | Develop custom detections to identify compromised accounts, including new or unusual access behaviors. | Partially Available | Stage 3 - Innovative |  | Insider Threat Team | Improve detection algorithms; Expand monitoring to all critical assets | Account Compromise Detection, Threat Response
Training & Education | Security Training Feedback | Provide feedback to enhance awareness and build the yearly Security training program. | Available | Stage 2 - Procedural |  | Training & Awareness Team | Develop specialized insider threat training modules; Collect feedback from participants | Awareness Training, Risk Reduction
Operational | Threat and Trend Documentation | Process and document emerging threats and trends related to insider activity, including their impact on business processes. | Available | Stage 3 - Innovative |  | Insider Threat Team | Develop detailed documentation standards; Improve accessibility for business units | Threat Documentation, Risk Management
Operational | Detection Testing | Test custom detections for functionality and quality assurance to ensure effectiveness in real scenarios. | Available | Stage 3 - Innovative |  | Quality Assurance Team | Automate testing procedures; Establish regular testing intervals | Quality Assurance, Incident Response
Operational | Business Unit Outreach | Outreach to high-impact Business Units for support, including proactive monitoring and addressing specific concerns. | Available | Stage 2 - Procedural |  | Insider Threat Team | Develop a formal outreach program; Address BU-specific risks in outreach efforts | Stakeholder Engagement, Risk Mitigation
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## Team
Category | Sub-Item | Description | Availability | Maturity Level | Target Level | Owner | Improvement Plan | Use Cases
Team Engagement | Regular Team Events | Regular team events and activities to keep employees engaged and foster team bonding. | Available | Stage 3 - Innovative |  | HR Team | Organize more diverse events; Solicit feedback on event types | Team Engagement, Morale Boost
Team Engagement | Recognition Programs | Implement recognition programs to appreciate individual and team achievements. | Partially Available | Stage 2 - Procedural |  | HR & Team Leads | Develop a structured recognition plan; Include peer-to-peer recognition | Employee Satisfaction, Motivation
Training & Development | Skill Development Training | Provide regular training to develop technical and soft skills, including certifications and workshops. | Available | Stage 3 - Innovative |  | Training & Development Team | Expand training offerings based on team needs; Develop personalized growth plans | Skill Enhancement, Career Growth
Training & Development | Cross-Training Opportunities | Facilitate cross-training sessions to share knowledge across different roles and improve adaptability. | Partially Available | Stage 2 - Procedural |  | Team Leads | Schedule regular cross-training sessions; Encourage participation in other domains | Knowledge Sharing, Team Resilience
Work-Life Balance | Flexible Work Hours | Offer flexible work hours to allow team members to balance personal and professional responsibilities. | Available | Stage 3 - Innovative |  | HR Team | Expand options for flexible hours; Gather feedback from employees on work-life balance | Employee Well-being, Retention
Work-Life Balance | Remote Work Support | Provide resources and support for remote work, including equipment and allowances for remote productivity. | Available | Stage 3 - Innovative |  | IT & HR Team | Improve remote work setup based on feedback; Provide ergonomic support | Work-Life Balance, Productivity
Time Off | Encouraging Time Off | Encourage team members to take time off to prevent burnout and maintain productivity. | Available | Stage 2 - Procedural |  | Team Leads & HR Team | Develop a communication strategy promoting the importance of time off | Employee Well-being, Burnout Prevention
Project Engagement | Project Selection Input | Allow team members to provide input on the types of projects they are interested in working on. | Partially Available | Stage 2 - Procedural |  | Project Managers | Develop a system for capturing preferences; Align projects with individual growth goals | Employee Satisfaction, Project Ownership
Project Engagement | Regular Project Updates | Provide regular updates on project progress, including challenges and wins, to keep everyone informed. | Available | Stage 3 - Innovative |  | Project Managers | Standardize the format for project updates; Solicit feedback on update content | Transparency, Team Engagement
Personal Growth & Development | Individual Development Plans | Work with team members to create individual development plans tailored to their career goals. | Available | Stage 3 - Innovative |  | Team Leads | Formalize development plan reviews; Link growth plans with training opportunities | Career Growth, Retention
Personal Growth & Development | Mentorship Program | Establish a mentorship program pairing experienced employees with newer team members for guidance. | Partially Available | Stage 2 - Procedural |  | HR & Senior Team Members | Expand mentorship opportunities; Formalize mentor-mentee expectations | Knowledge Transfer, Employee Engagement
Hiring & Recruitment | Competitive Pay | Offer competitive pay aligned with industry standards to attract and retain top talent. | Available | Stage 3 - Innovative |  | HR Team | Conduct regular market salary reviews; Adjust pay to meet or exceed benchmarks | Talent Attraction, Employee Retention
Hiring & Recruitment | Benefits Package | Provide comprehensive benefits, including health insurance, retirement plans, and wellness programs. | Available | Stage 3 - Innovative |  | HR Team | Regularly review and enhance benefits based on employee needs; Benchmark against competitors | Employee Well-being, Talent Retention
Hiring & Recruitment | Hiring Process Improvement | Continuously improve the hiring process to ensure efficiency, inclusivity, and a positive candidate experience. | Partially Available | Stage 2 - Procedural |  | Recruitment Team | Collect candidate feedback; Implement improvements for a streamlined hiring process | Candidate Experience, Hiring Efficiency
Hiring & Recruitment | Onboarding Experience | Develop a structured onboarding program to help new hires integrate into the company culture and become productive quickly. | Available | Stage 3 - Innovative |  | HR Team | Automate onboarding processes; Provide tailored onboarding content for different roles | New Hire Integration, Employee Engagement
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## Compliance & Audit
Capability | Sub-Item | Description | Availability | Maturity Level | Target Level | Owner | Improvement Plan | Use Cases
Policy Management | Compliance Policy Implementation | Implementation of compliance policies (e.g., GDPR, HIPAA) to meet regulatory requirements | Available | Stage 3 - Innovative |  | Compliance Team | Regular policy updates based on regulatory changes | Compliance Adherence, Regulatory Coverage
Policy Management | Documentation and Revision Control | Maintain up-to-date compliance documentation, including version control for revisions | Partially Available | Stage 2 - Procedural |  | Compliance Team | Automate version control processes and regular document audits | Compliance Readiness, Audit Preparation
Audit Readiness | Internal Audit Preparation | Prepare for internal audits with regular assessments of compliance status | Available | Stage 2 - Procedural |  | Compliance Team | Develop standardized internal audit checklists | Audit Readiness, Compliance Verification
Audit Readiness | External Audit Support | Support external auditors by providing requested documentation and access to systems | Available | Stage 3 - Innovative |  | Compliance & IT Team | Automate audit documentation generation; Develop relationships with auditors | Regulatory Compliance, Audit Facilitation
Risk Assessment | Compliance Risk Assessment | Conduct compliance risk assessments to identify and mitigate risks | Available | Stage 3 - Innovative |  | Risk Management Team | Automate risk assessment with regular updates | Risk Management, Compliance Monitoring
Monitoring & Reporting | Compliance Monitoring | Continuous monitoring of compliance requirements through automated tools | Partially Available | Stage 3 - Innovative |  | IT & Compliance Team | Expand monitoring capabilities to cover new compliance requirements | Real-Time Compliance, Risk Management
Monitoring & Reporting | Audit Trail Maintenance | Maintain an audit trail of user activities related to compliance-sensitive areas | Available | Stage 3 - Innovative |  | IT Security Team | Automate and centralize audit trail generation and storage | Compliance Verification, Incident Review
Data Management | Data Classification | Classify sensitive data for compliance purposes to ensure appropriate handling | Partially Available | Stage 2 - Procedural |  | Data Management Team | Implement more detailed data classification policies | Data Security, Compliance Adherence
Data Management | Data Retention Policies | Implement data retention policies in line with regulatory requirements | Available | Stage 3 - Innovative |  | Compliance & IT Team | Automate data retention enforcement | Data Privacy, Legal Compliance
Awareness & Training | Compliance Training | Regular training for staff on compliance policies and responsibilities | Available | Stage 2 - Procedural |  | Training Team | Develop compliance-specific training modules; Improve training frequency | Employee Awareness, Risk Reduction
Awareness & Training | Awareness Campaigns | Launch awareness campaigns about new compliance requirements and changes | Available | Stage 2 - Procedural |  | Compliance & HR Team | Develop awareness content for different departments; Gather feedback on campaigns | Employee Engagement, Compliance Adherence
Tools & Automation | Compliance Management Tools | Utilize tools for managing compliance requirements and reporting | Partially Available | Stage 3 - Innovative |  | IT & Compliance Team | Expand tool integration capabilities; Automate reporting | Compliance Tracking, Efficiency
Tools & Automation | Audit Automation | Automate audit workflows, including data collection, reporting, and document submission | Partially Available | Stage 2 - Procedural |  | Compliance Team | Implement automated workflows for audit support | Audit Readiness, Process Improvement
Incident Management | Compliance Violation Handling | Define and manage workflows for responding to compliance violations | Available | Stage 3 - Innovative |  | Incident Response Team | Develop predefined playbooks for handling common compliance violations | Regulatory Compliance, Incident Response
Incident Management | Breach Reporting | Ensure timely reporting of breaches as per regulatory requirements | Available | Stage 3 - Innovative |  | Incident Response Team | Automate breach reporting mechanisms and notification workflows | Compliance, Regulatory Reporting
Project Tracking
Year 1
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 2
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Project Tracking
Year 3
January |  |  | February |  |  | March
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
April |  |  | May |  |  | June
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
July |  |  | August |  |  | September
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
October |  |  | November |  |  | December
Capability | Sub-Item | Description | Capability | Sub-Item | Description | Capability | Sub-Item | Description
Resource Management and Future Planning
Resource Type | Details | Current Usage | Projected Growth (1 Year) | Projected Growth (3 Years) | Cost Tracking
Servers/Infrastructure | Number of servers required to run the SIEM, including specifications (CPU, RAM, storage). | 5 servers | 20% | 50% | 15000
Deployment Type | Cloud-based, On-Premises, or SaaS. | Cloud-Based | Move to hybrid model | Full hybrid implementation | 10000
People Required | Number of people needed to manage, monitor, and maintain the SIEM. | 5 FTEs | 2 | 5 | $500,000 annually
Teams Involved | Teams responsible for infrastructure, operations, patching, upgrades, support, etc. | Infra, Ops, Sec | Add DevOps support | Expand SecOps involvement | N/A
User Base | Number of end-users using the SIEM for monitoring, analysis, or reporting. | 50 Analysts | 10 | 30 | Training costs
Support Staff | Roles and responsibilities of those who support the system (e.g., SOC analysts, engineers). | 3 Engineers | 1 | 3 | $150,000 annually
Patching & Updates | Frequency of patching, who is responsible, and whether updates are automated or manual. | Monthly | Automate half of updates | Fully automated | $5,000 annually
Upgrades/Capacity Planning | Frequency and process for upgrades, and how capacity is monitored and scaled. | Bi-Annual | Move to quarterly reviews | Dynamic scaling setup | 20000
Training Requirements | Training required for various teams to effectively use and manage the SIEM. | Ongoing | Add threat hunting modules | Expand ML capabilities | $10,000 annually
Tooling and Integrations | Additional tools and integrations that are needed to support the SIEM environment. | Multiple tools | Add new SOAR integrations | Full automation integration | $30,000 annually
Future Usage Projections | Expected increase in infrastructure, users, and overall system complexity over the next 1-3 years. |  | +30% in resources | +50% in resources | $50,000
Future Cost Estimates | Projected costs for scaling, training, maintenance, and upgrades over the next 1-3 years. |  | 100000 | 150000

## SIEM Score Card
Feature Category | Requirement | Description/Example | Current Platform | Vendor 1 | Vendor 2 | Vendor 3
Core Features | Search Functionality | Ability to upload a CSV file to be used in the search
Core Features | Search Functionality | Ability to save results in a CSV file for additional searches or export
Core Features | Parse Using Regex | Ability to use Regex to parse out additional fields
Core Features | Nested Searches | Ability to perform nested searches
Core Features | CIDR Match | CIDR match search feature for IP ranges
Core Features | In-Search Fields Creation | Ability to create new fields in-line in the search
Core Features | Scheduled Reports/Alerts | Ability to create scheduled reports/alerts to perform additional actions
Core Features | Search Functionality | A well-defined and documented search language
Data Visualizations | Customized Dashboard Panels | Ability to customize dashboard panels
Data Visualizations | Filtering | Drop down to filter results based on field value
Data Visualizations | Dynamic Data Entry | Dynamic data entry to populate dashboard searches
Data Visualizations | Custom Time Ranges | Custom time ranges for visualizations
Data Visualizations | Drill-Down | Drill-down feature to provide additional information
Data Visualizations | Role-Based Access | Provide role-based access
Data Visualizations | Color Coded Visualization | Add color-coded visualizations based on field values
Data Processing | Data Models | Reduce data to smaller sets for faster searches on normalized data sets
Data Processing | Common Information Model | Apply a Common Information Model to data sets to normalize searches
Data Processing | Role-Based Access | Provide role-based access to data sets
Data Processing | New Indexes | Create new indexes based on output of search results
Data Processing | Inter-Operability | Ability to send/receive data to/from other tools
Data Processing | Log Onboarding | Ability to add new data sources, identify data types and natively parse fields (with/without packs/add-ons/libraries)
Advanced Features Sets | Risk Framework | Assets and Identities management for dynamic risk scoring
Advanced Features Sets | Risk Modifiers | Risk Modifiers to increase/decrease risk score based on criteria
Advanced Features Sets | Risk Index/Data Model | Ability to create a Risk Index/Risk Data Model to aggregate events
Advanced Features Sets | MITRE ATTACK Framework | MITRE ATTACK framework mappings and data enrichment
Threat Intelligence | Intelligence Feeds | Framework for managing threat intelligence feeds
Alert Management | Unified Alert View | Single pane of glass to see and manage all alerts triggered
Alert Management | Alert Status Management | Change status of alerts during investigation
Alert Management | Alert Enrichment | Enrich alerts via asset/user data, drilldowns, threat intel, etc
Alert Management | New Alerts Creation | Easily create new alerts
Alert Management | Content Packs | Vendor-provided content packs with prebuilt detections
Alert Management | Role-Based Alert Management | Role-based access to alert creation, modification, and deletion
Alert Management | Version Control for Detections | Version control tracking for detections
SOAR Integration | Automation Platforms Integration | Send/receive events with automation platforms
SOAR Integration | Search from SOAR | Ability to perform additional searches from SOAR platform
Asset and Identities | Asset Mapping | Ability to map an asset to an IP address from data sources
Asset and Identities | Asset Import | Ability to import assets
Asset and Identities | Identity Import | Ability to import identities
Miscellaneous | Information Sharing | Active user group/community for information sharing and support
Miscellaneous | Training | Availability of free education/training material
Miscellaneous | DevOps Environment | Ability to stand up Dev environment without additional cost
Admin | Role-Based Access | Restrict access to indexes/data based on access requirements
Admin | Log Data Processor Integration | Integration with log data processors
Admin | Correlation Searches | Ability to perform correlation searches across data sets
Admin | Audit | Allow admins to audit user actions
Admin | Data Onboarding Support | Support various forms of data onboarding

## Email Security Score Card
Feature Category | Requirement | Description/Example | Current Platform | Vendor 1 | Vendor 2 | Vendor 3
Core Email Security Features | Spam Filtering | Ability to filter spam emails effectively
Core Email Security Features | Phishing Detection | Detect and quarantine phishing emails
Core Email Security Features | Malware Attachment Detection | Detect malicious attachments and remove them from emails
Core Email Security Features | URL Protection | Protect users from malicious URLs embedded in emails
Core Email Security Features | Domain Spoofing Prevention | Detect and block emails with spoofed domains
Core Email Security Features | DKIM Enforcement | Enforce DomainKeys Identified Mail (DKIM) to validate email integrity
Core Email Security Features | SPF Enforcement | Enforce Sender Policy Framework (SPF) to verify sending server authenticity
Core Email Security Features | DMARC Enforcement | Enforce Domain-based Message Authentication, Reporting & Conformance (DMARC) to prevent domain spoofing
Threat Intelligence Integration | Threat Intelligence Feeds | Integrate threat intelligence feeds for updated phishing campaigns
Threat Intelligence Integration | Phishing Indicators Update | Regular updates of phishing indicators such as domains, IPs, and URLs
User Awareness & Training | Phishing Simulation | Conduct phishing simulation campaigns to educate employees
User Awareness & Training | User Training Modules | Provide user training modules on email security and phishing awareness
User Awareness & Training | Reporting Button | Provide an easy-to-use button for reporting suspicious emails
Automated Response Capabilities | Automated Quarantine | Automatically quarantine emails identified as phishing or spam
Automated Response Capabilities | Remediation Playbooks | Pre-built remediation playbooks to handle phishing incidents
Policy Management | Customizable Policies | Ability to create customizable policies for filtering and protection
Policy Management | Role-Based Access | Role-based access to manage email security policies
Monitoring & Analytics | Dashboard for Threat Monitoring | Real-time dashboard to monitor threats and email security status
Monitoring & Analytics | Reporting Capabilities | Generate reports on phishing, spam, and other email threats
Monitoring & Analytics | Executive Summary | Provide executive-level summaries for email security
Incident Management | Incident Response Workflow | Ability to define and manage incident response workflows for email threats
Incident Management | Alerting for Critical Incidents | Trigger alerts for critical incidents detected in emails
Integration with SOAR | Automated Playbook Execution | Execute automated playbooks in response to detected phishing incidents
Integration with SOAR | Threat Enrichment | Enrich email threats with additional data from external sources
Miscellaneous Features | Secure Email Gateway | Secure email gateway capabilities to inspect inbound and outbound traffic
Miscellaneous Features | Archiving and Compliance | Archive emails and ensure compliance with industry standards
Miscellaneous Features | Integration with M365 or GSuite | Seamless integration with popular platforms like Microsoft 365 or GSuite
Miscellaneous Features | Information Sharing Community | Participate in community forums for threat information sharing
Miscellaneous Features | Free Training Availability | Availability of free training materials for email security awareness
Admin | Audit Logs for Admin Actions | Maintain audit logs for administrative actions on the email security platform
Admin | User Activity Monitoring | Monitor user activity related to email security actions
Admin | Role-Based Admin Access | Restrict admin actions based on roles to ensure appropriate control

## Network Sec. Score Card
Feature Category | Requirement | Description/Example | Current Platform | Vendor 1 | Vendor 2 | Vendor 3
Intrusion Detection System (IDS) | Network Traffic Analysis | Ability to monitor and analyze network traffic for suspicious activities
Intrusion Detection System (IDS) | Signature-Based Detection | Use of signature-based detection methods to identify known threats
Intrusion Detection System (IDS) | Anomaly-Based Detection | Use of anomaly-based detection to identify unusual network behavior
Packet Capture & Storage | Full Packet Capture | Ability to capture full network packets for detailed analysis
Packet Capture & Storage | Long-Term Storage | Store packet captures for long-term forensics and analysis
Packet Capture & Storage | Indexed Packet Search | Ability to search packet captures using indexed search capabilities
Filtering & Blocking Policies | Layer 7 Application Filtering | Ability to filter traffic based on application layer information
Filtering & Blocking Policies | Custom Block/Allow Lists | Ability to create custom block/allow lists for network traffic
Filtering & Blocking Policies | Geo-IP Filtering | Block or allow traffic based on geographic IP location
Automation | Dynamic Block List Updates | Automatically update block lists based on threat intelligence
Automation | Allow/Deny List Automation | Automation to add IP addresses or domains to allow/deny lists based on criteria
Threat Intelligence Integration | Network Threat Feeds | Integrate threat intelligence feeds for network threat detection
Threat Intelligence Integration | Threat Indicator Correlation | Correlate threat indicators with network traffic to detect threats
Network Access Control (NAC) | Role-Based Network Access | Implement role-based network access policies to limit user access
Network Access Control (NAC) | Endpoint Compliance Checks | Check endpoint compliance before granting network access
DDoS Protection | Traffic Scrubbing | Ability to scrub malicious traffic during a Distributed Denial of Service (DDoS) attack
DDoS Protection | Real-Time Monitoring | Monitor traffic in real-time for signs of DDoS attacks
DDoS Protection | Automated Mitigation | Automatically mitigate DDoS attacks based on pre-defined thresholds
VPN and Encryption | Secure VPN Access | Provide secure VPN access for remote users
VPN and Encryption | Encryption Standards | Ensure encryption standards such as AES-256 for secure communication
Firewall Management | Stateful Inspection | Perform stateful inspection of network traffic for deeper analysis
Firewall Management | Zone-Based Segmentation | Segment network using zone-based firewall rules
Firewall Management | High Availability Configurations | Support high availability and redundancy in firewall setups
Monitoring & Analytics | Network Traffic Visualization | Visualize network traffic for easy understanding of flow and potential threats
Monitoring & Analytics | Alerting for Network Anomalies | Trigger alerts for any detected network anomalies
Monitoring & Analytics | Dashboard for Network Security | Provide a real-time dashboard for monitoring network security posture
Miscellaneous Features | Integration with SIEM | Integrate with SIEM for centralized monitoring and correlation of network events
Miscellaneous Features | API Integration | Provide API for integration with other security tools
Admin | Audit Logging | Maintain audit logs of changes to network security configurations
Admin | Role-Based Admin Access | Restrict administrative actions based on roles
Admin | Configuration Backups | Regularly backup network security configurations for quick recovery

## EDR
Feature Category | Requirement | Description/Example | Current Platform | Vendor 1 | Vendor 2 | Vendor 3
Core Antivirus Features | Real-Time Protection | Ability to provide real-time protection against viruses and malware
Core Antivirus Features | On-Demand Scanning | Perform manual or scheduled scans for viruses and malware
Core Antivirus Features | Signature-Based Detection | Use of signature-based detection methods to identify known threats
Core Antivirus Features | Heuristic Analysis | Use heuristic analysis to detect unknown or zero-day threats
Core Antivirus Features | Quarantine Management | Ability to quarantine, release, or delete infected files
Endpoint Detection & Response (EDR) | Behavioral Analysis | Detect suspicious activities based on behavioral analysis
Endpoint Detection & Response (EDR) | Threat Hunting | Enable proactive threat hunting across endpoints
Endpoint Detection & Response (EDR) | Incident Response | Provide automated or guided response actions for detected threats
Endpoint Detection & Response (EDR) | Real-Time Evidence Collection | Collect evidence from endpoints in real time during incident response
Endpoint Detection & Response (EDR) | Root Cause Analysis | Perform root cause analysis to understand the origin of an attack
Threat Intelligence Integration | Threat Intelligence Feeds | Integrate threat intelligence feeds to enhance detection capabilities
Threat Intelligence Integration | Threat Enrichment | Enrich alerts with additional threat context from external sources
Automation | Automated Remediation | Automate the remediation of detected threats based on predefined rules
Automation | Dynamic Block Lists | Automatically update block lists based on detected threats
Monitoring & Reporting | Centralized Management Console | Provide a centralized management console for monitoring and management
Monitoring & Reporting | Alerting and Notifications | Generate alerts and notifications for detected threats
Monitoring & Reporting | Executive Reporting | Provide executive-level summary reports on threat status
Policy Management | Customizable Policies | Ability to create and customize security policies for different endpoints
Policy Management | Role-Based Access | Role-based access to manage endpoint security policies
Integration | Integration with SIEM | Integrate with SIEM for centralized threat monitoring and correlation
Integration | Integration with SOAR | Integrate with SOAR for automated response capabilities
Miscellaneous Features | Offline Protection | Provide protection for endpoints that are offline or not connected to the network
Miscellaneous Features | Device Control | Control access to external devices such as USB drives
Miscellaneous Features | Application Allow/Deny listing | Ability to allow/deny list applications to prevent unauthorized execution
Admin | Audit Logging | Maintain audit logs of changes to endpoint security configurations
Admin | Role-Based Admin Access | Restrict administrative actions based on roles
Admin | Configuration Backups | Regularly backup endpoint security configurations for quick recovery