## Program Overview
Metric Name | Current Stage | Target Stage | Description | Target Description | Status | Responsible Party | Timeline | Priority | Comments | Risk Assessment | Mitigation Plan | Budget | Tools | Challenges
SIEM Capability | Stage 2 | Stage 4 | Basic SIEM monitoring in place, with some alerts | Full automation of detection & response | In Progress | SIEM Engineer |  | High | Need to integrate threat feeds | High
SOAR Capability | Stage 1 | Stage 2 | Automation and enrichment to support investigations and response | 70% automated reposne for teir 1 investigations | In Progress | SOAR Engineer |  | High | Automation requires integration with SIEM
Incident Response | Stage 3 | Stage 4 | Advanced playbooks, some manual responses | Full automation of response workflows | On Track | Incident Response Team |  | High |  | Medium
Log Collection | Stage 1 | Stage 3 | Limited to basic network device logging | Coverage for all critical assets | At Risk | SIEM Engineer |  | Medium | Need additional resources to add VPN logging | Low
Threat Intelligence | Stage 0 | Stage 3 | No integration of threat intelligence feeds | Integrate at least two commercial threat feeds | Not Started | Threat Intel |  | High | Identifying appropriate threat feeds | Low
Team | Stage 2 | Stage 4 | Overall team capabilities needed to meet current and future threat landscapes | All programs staffed at 80% or higher, training in place for development, retention programs in place, on going process improvements and program development | In Progress | Leadership Team |  | High |  | High
Compliance/Audit Reddiness | Stage1 | Stage 3 | Ability to meet all legal and compliance requirements, provide audit evedince effcentely, and in timely manner | Automation in place for self-service style audit evedience collection, dashboards for compliance monitoring, minimal effort required to support audits | In Progress | SIEM Engineer |  | Medium |  | Medium
Stage | Description
Stage 0 - Initial | General Awareness of the topic but no initiatives are in place.
Stage 1 - Minimal | There are basic things in place to meet an initial requirement. This is entry level and more work is needed.
Stage 2 - Procedural | This area has begun to evolve and improvements have been made. At this level the initiative begins to exceed the minimum requirement.
Stage 3 - Innovative | This area begins to see advanced improvements and is well established. At this level the initiative is considered advanced and exceeds the requirement.
Stage 4 - Leading | This area is well established and mature, only basic maintenance is required. At this level the initiative is cutting edge and beyond industry standards.

## Log Collection
Data Source Name | Log Type | Availability | Required? | Compliance Requirements | Log Volume (GB/day) | Data Quality | Retention Period | Use Cases | Current Issues | Improvement Plan | Owner | Collection Status | Data Integration Status | Data Format | Maturity Level
Firewall Logs | Network | Available | Yes |  | 50 | High | 1 Year | Threat Detection, Compliance | None | N/A | Network Team | Automated | Integrated | Syslog | Stage 3 - Innovative
VPN Logs | Security | Partially | Yes |  | 10 | Medium | 90 Days | Access Auditing, User Monitoring | Missing logs from some devices | Add additional VPN log collectors | Security Team | Manual | Not Integrated | JSON | Stage 1 - Minimal
DNS Logs | Network | Unavailable | Yes |  | Unknown | N/A | N/A | Threat Detection | No collection mechanism | Implement centralized DNS logging | Network Operations | Not Collected | Not Integrated | N/A | Stage 0 - Initial
Router & Switch Logs | Network | Partially | Yes |  | 20 | Medium | 180 Days | Network Monitoring, Troubleshooting | Missing some device logs | Standardize logging across devices | Network Team | Manual | Not Integrated | Syslog | Stage 1 - Minimal
Proxy Logs | Network | Available | Yes |  | 15 | High | 1 Year | Web Usage Monitoring, Threat Detection | None | N/A | Security Team | Automated | Integrated | CSV | Stage 3 - Innovative
Network IDS/IPS Logs | Security | Available | Yes |  | 25 | High | 1 Year | Intrusion Detection, Threat Prevention | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative
NetFlow/SFlow | Network | Available | Yes |  | 30 | Medium | 90 Days | Traffic Analysis | Data volume is very high | Implement filtering to reduce volume | Network Team | Automated | Not Integrated | NetFlow | Stage 2 - Procedural
Endpoint Security (EDR) | Security | Available | Yes |  | 100 | High | 180 Days | Threat Detection, Response | Data duplication | Streamline logging to reduce redundancy | Endpoint Team | Automated | Integrated | JSON | Stage 3 - Innovative
Antivirus/Anti-Malware Logs | Security | Available | Yes |  | 5 | High | 90 Days | Malware Detection | None | N/A | Endpoint Team | Automated | Integrated | CSV | Stage 3 - Innovative
Patch Management Logs | Endpoint | Available | Yes |  | 2 | Medium | 180 Days | Vulnerability Management | Inconsistent logging from some endpoints | Standardize patch reporting | Endpoint Team | Manual | Partially Integrated | CSV | Stage 2 - Procedural
Web Server Logs | Application | Available | No |  | 20 | Medium | 30 Days | Debugging, Monitoring | Incomplete log entries | Standardize logging practices | DevOps Team | Automated | Not Integrated | CSV | Stage 1 - Minimal
Application Server Logs | Application | Available | Yes |  | 25 | Medium | 90 Days | Application Monitoring, Troubleshooting | None | N/A | Application Team | Automated | Partially Integrated | JSON | Stage 2 - Procedural
Database Audit Logs | Application | Available | Yes |  | 15 | High | 1 Year | Compliance, User Activity Tracking | None | N/A | Database Admin Team | Automated | Integrated | JSON | Stage 3 - Innovative
Authentication Services Logs | Identity | Available | Yes |  | 10 | High | 1 Year | User Authentication, Access Control | None | N/A | Identity Management Team | Automated | Integrated | CSV | Stage 3 - Innovative
Identity Provider Logs | Identity | Available | Yes |  | 8 | High | 180 Days | Authentication Tracking, MFA | None | N/A | Identity Team | Automated | Integrated | JSON | Stage 3 - Innovative
Privileged Access Management Logs | Identity | Available | Yes |  | 5 | High | 90 Days | Privileged Session Monitoring | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative
SIEM System Logs | Security | Available | Yes |  | 10 | High | 1 Year | System Monitoring, Alerting | None | N/A | SIEM Admin Team | Automated | Integrated | JSON | Stage 3 - Innovative
SOAR Logs | Security | Available | Yes |  | 5 | High | 90 Days | Incident Response Automation | None | N/A | Security Operations | Automated | Integrated | JSON | Stage 3 - Innovative
Vulnerability Scanners | Compliance | Available | Yes |  | 15 | High | 1 Year | Vulnerability Management, Compliance | None | N/A | Security Team | Automated | Integrated | CSV | Stage 3 - Innovative
CloudTrail (AWS) | Cloud | Available | Yes |  | 15 | High | 180 Days | Cloud Activity Monitoring, Compliance | None | N/A | Cloud Team | Automated | Integrated | JSON | Stage 3 - Innovative
GuardDuty (AWS) | Cloud Security | Available | Yes |  | 8 | High | 90 Days | Anomaly Detection in Cloud | Limited to certain accounts | Expand to cover all accounts | Cloud Security Team | Automated | Partially Integrated | JSON | Stage 2 - Procedural
Storage Access Logs (S3) | Cloud | Available | Yes |  | 5 | High | 90 Days | Data Access Monitoring | None | N/A | Cloud Team | Automated | Integrated | JSON | Stage 3 - Innovative
Badge Access Logs | Physical | Available | No |  | 5 | High | 1 Year | Physical Security Monitoring | None | N/A | Facilities Team | Automated | Not Integrated | CSV | Stage 1 - Minimal
Enterprise Resource Planning (ERP) System Logs (SAP) | Business | Available | Yes |  | 12 | Medium | 1 Year | Financial Monitoring, Compliance | None | N/A | Business Systems Team | Automated | Partially Integrated | JSON | Stage 2 - Procedural
CRM Logs (Salesforce) | Business | Available | No |  | 10 | Medium | 90 Days | Customer Activity Tracking | None | N/A | Sales Team | Automated | Not Integrated | CSV | Stage 1 - Minimal
Threat Intelligence Feeds | Security | Available | Yes |  | N/A | High | Real-time | Threat Detection, Indicator Matching | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative
Data Loss Prevention Logs | Security | Available | Yes |  | 5 | High | 90 Days | Sensitive Data Protection | None | N/A | Security Team | Automated | Integrated | JSON | Stage 3 - Innovative

## SIEM
Capability | Sub-Items | Description | Availability | Maturity Level | Owner | Improvement Plan | Use Cases
Detection Capabilities | Malware Detection, Anomaly Detection, Insider Threat Detection | Ability to detect various threats, such as malware, anomalies, and insider threats using the SIEM. Includes correlation of data from multiple sources to identify complex attack patterns. | Partially Available | Stage 2 - Procedural | SIEM Team | Improve detection rules for insider threats; Enhance correlation capabilities | Threat Detection, Compliance
Threat Hunting | IOC Search, Behavioral Analysis, Threat Hypothesis Testing | Ability to proactively search for indicators of compromise (IOCs) and unknown threats. Involves using both automated tools and manual analysis to detect stealthy or sophisticated attacks. | Available | Stage 3 - Innovative | Threat Intel Team | Increase frequency of threat hunts; Develop more advanced threat hunting playbooks | Threat Detection, Incident Response
Custom Dashboards | Executive Dashboard, Analyst Dashboard, Incident Response Dashboard | Customizable dashboards to monitor specific activities or use cases. Provides detailed views for different stakeholders, such as executives, analysts, and incident responders. | Available | Stage 3 - Innovative | SIEM Admin Team | Develop more user-specific dashboards; Create dashboards for executive reporting | Visibility, Reporting, Compliance
Alert Creation | Rule-Based Alerts, Threshold Alerts, Escalation Workflows, Machine Learning Alerts | Ability to create and manage alerts for suspicious activities detected in logs. Includes advanced customization of alert logic, machine learning-based alerts, and escalation workflows based on severity. | Available | Stage 3 - Innovative | SOC Team | Refine alert thresholds to reduce false positives; Implement alert prioritization based on risk | Threat Detection, Incident Response
Admin Functions | User Management, Log Retention, Role-Based Access Control, Configuration Auditing | Administrative tasks such as user management, log retention, configuration changes, and auditing configurations. Includes role-based access control, audit logging, and periodic review of permissions. | Available | Stage 3 - Innovative | SIEM Admin Team | Streamline user role assignment; Automate audit logging for configuration changes | System Management, Compliance
Upkeep | Software Updates, Performance Monitoring, Health Checks, Backup & Recovery | Regular maintenance, software updates, and system health checks for the SIEM. Includes monitoring for performance bottlenecks, ensuring timely software patches, and backup & recovery processes. | Available | Stage 2 - Procedural | SIEM Maintenance Team | Automate routine maintenance tasks; Implement proactive health checks; Ensure regular backup and recovery tests | System Stability, Compliance
Threat Intel Feed Search | Feed Integration, Threat Correlation, Automated Enrichment, Threat Actor Profiling | Capability to search for and correlate threat intelligence feeds with internal activity to identify threats. Supports integration with multiple threat feeds, automated enrichment of indicators, and threat actor profiling. | Available | Stage 3 - Innovative | Threat Intel Team | Integrate additional threat feeds; Automate enrichment of threat intelligence data; Expand threat actor profiling capabilities | Threat Detection, Threat Intelligence

## Insider Risk
Category | Description | Stage 0 | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage | Description
Administrative | Corporate Policies in place that support monitoring, investigations, and remediation efforts. Policies are reviewed for changes Feedback is provided to strengthen/enhance policies | [5 empty] | Stage 0 - Initial | General Awareness of the topic but no initiatives are in place.
| Partnerships in place with Legal, Employee Relations, and Privacy teams. Briefed on new legal and regulatory requirements/considerations Ensure process to remediate Insider Threat activity is in place | [5 empty] | Stage 1 - Minimal | There are basic things in place to meet an initial requirement. This is entry level and more work is needed.
| Obtain support from Senior Leadership team, provide regular updates, and solicit feedback | [5 empty] | Stage 2 - Procedural | This area has begun to evolve and improvements have been made. At this level the initiative begins to exceed the minimum requirement.
| Relevant logs are being collected to support Use Cases. Log sources are reviewed on a regular basis and updated as required. Logging Standards are reviewed on a regular basis and updated as required. | [5 empty] | Stage 3 - Innovative | This area begins to see advanced improvements and is well established. At this level the initiative is considered advanced and exceeds the requirement.
| Threat Landscape is well documented. Reviewed and Updated at regular intervals | [5 empty] | Stage 4 - Leading | This area is well established and mature, only basic maintenance is required. At this level the initiative is cutting edge and beyond industry standards.
Tools | Data Loss Prevention (DLP) tools are in place and being monitored. The tool's alert portfolio is reviewed at regular intervals The tool is tested on a regular basis to determine effectiveness
Use Behavior Analytic (UBA/UEBA) are in place and being monitored. The tool's alert portfolio is reviewed at regular intervals The tool is tested on a regular basis to determine effectiveness
Risk Based Alerting (RBA) framework is in place. Risk rules are reviewed at regular intervals Risk rules are tested on a regular basis to determine effectiveness
Custom Detections | Custom detections are being developed and monitored for sensitive file exfiltration.
Custom detections are being developed and monitored for rogue administrator activity. Possible malicious changes Unusual user activity review preforming tasks that are out of scope
Custom detections are being developed and monitored for unusual file access. User list is updated at regular intervals Process in place to report unusual/suspicious activity to required teams
Monitoring departments with high turn over rates.
Custom detections to detect possible compromised accounts. new/unusual access behavior new/unusual file access
Provide enhanced monitoring for employees with Government clearances.
Training & Education | Provide feedback to address and build awareness for yearly Security training program.
Operational | Process and document emerging threats and trends.
Test detections for functionality and quality assurance.
Outreach to high impact Business Units for additional support. Proactive monitoring high turnover teams Address BU specific concerns